## Tabelle1
ISO 56000
Product definition Process (PdP)
Initial Process | 4i´s concept development |  |  |  | Project Approval
| Step 1: Form and describe the Idea | Step 2: concept | Step 3. fine adjustment of concept | Step 4: Concept prove out | MS 0
| Proceed | Proceed | Proceed | Proceed
Select 3to 5 idea's from Idea pool | Describe main function | Provide product Concept | Provide detailed system description | Assemble process | Project hand book
Describe application | Pre BOM and materials / consider HS standards | Provide function matrix / block | Provide sub elements / components standards | Test function | SOW
Outstanding items | Initiate cost tracking / assumption | Provide key items | Virtual function test | Test miss use | Rasic
Market opportunities | Market situation and trend investigation | Complete BOM and Materials with confirmed sources | Virtual test of robustness of design | Design Review | Stockholder analyse
Competitor situation | Which main technical and safety standards are advised | Cost check concept verification | Feasibility confirmation |  | Team Resource Plan
Safety regulations | Are there major changes in the organisation required | Cost check project / Product / Resources / equipment / Infrastructure | Design review |  | Timing plan
Risks | New buildings and equipment required? | Complete technical risk analyse / concept verification plan | 3D and 2D |  | Risk and Opportunity matrix
Organisational need | On boarding of support required, list by function | Feasibility check | Electrical circuit layout |  | Handover to Program Team
Technical need | Are there similar ideas at competitor in progress? (benchmark) | Design Review | Preliminary program code
Materials and supply change | Estimate Idea PdP timeline | 3D
Cost estimation | Estimate project PEP timeline | Electrical circuit diagram
Provide decision | Estimate required resource | Software function & features
Misuse investigation
check IP
FuSi | Normungssituation (FuSi) gem Anwendung Systemdefinition (Item Definition) | Gefährdungsanalyse und Risikoanalyse (HARA / PHA) | Bestimmung des Sicherheitsintegritätslevels (SIL / ASIL | Definition der Sicherheitsziele (Safety Goals)
| document / output | document / output | document / output | document / output
| Provide team and stakeholder matrix | Team and stakeholder reports | Team and stakeholder reports | Team and stakeholder reports
| Issue Engineering and Safety Standard recommendation list | Engineering and Safety Standard tracker | Engineering and safety standard tracker | Confirmation of applicable engineering and safety standard | Product Development Specifications (Lastenheft)
|  | BOM -Material list | BOM -Material list confirmed | BOM complete
|  | Product KPI list | Product KPI list | Product KPI list confirmation
|  | risk tracker | Risk tracker | Risk analyses complete
| Product KPI list |  | System FMEA | System FMEA complete
|  | verification plan | Test and lab equipment order | Verification complete
|  | 3D | 3D and 2D | Hardware List and Layout
Preliminary program code (SW)
FuSi | Funktionsblock / Systemgrenzen / Environmental | HRA/ PHA | SIL / ASIL Level | Safety Goal's agreement list
| Open issue tracker | Open issue tracker | Open issue tracker | Open issue tracker
TGW / TGR
LL
|  | Cost tracker | Cost tracker | Cost tracker confirmation
|  | Prototype tooling and equipment list | Prototype tooling and equipment order | build open item list
Iteration Lop -Define -Plane -Test -Development-Accept-Review